## FY16
To be presented at October 2017 Town Meeting
Hi-lighted in yellow-Town Mngrs. Operating Budget (413,190)
| Red Highlighted are the Large Projects |  | 2017-01-31
| Blue Highlighted are CPC Projects | [9 empty] | PAST PROJECTS |  |  | 5 YEAR CAPITAL PLAN |  |  |  |  | 15 YEAR CAPITAL PLAN
Tracking ID | Project Description | 5-YR Plan | Department | Total Cost (FY15-FY29) | CK | Building Name or Vehicle Unit # | Project Type or Vehicle Type | Strategic Plan Group | Approved | Start/Duration | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | FY31 | FY32
5079 | Curtis Heating/Circulation Pumps and Motors |  | SPS/Facilities | 50000 | [5 empty] | FY18 | 5 YEAR CAPITAL PLAN FY18: 25000; 5 YEAR CAPITAL PLAN FY22: 50000
1003 | Town-wide Walkway Construction | Other Town wide | DPW | 1500000 | 1062810 | Town wide | Infrastructure | E | FY15 | FY15 | PAST PROJECTS FY15: 100000; PAST PROJECTS FY16: 100000; 5 YEAR CAPITAL PLAN FY18: 37190; 5 YEAR CAPITAL PLAN FY20: 100000; 5 YEAR CAPITAL PLAN FY21: 100000
GPS Survey Equipment | GPS Surveying Equipment |  | Engineering | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 38000
| Schools Cafeteria Kitchen Equipment |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 47000; 5 YEAR CAPITAL PLAN FY20: 40000; 15 YEAR CAPITAL PLAN FY24: 50000; 15 YEAR CAPITAL PLAN FY31: 50000
6001 | Town and Schools Carpet Replacement | Facilities/Town buildings | Facilities | 35000 | -323000 | Fairbank | Flooring | D |  | FY17 | PAST PROJECTS FY16: 108000; PAST PROJECTS FY17: 50000; 5 YEAR CAPITAL PLAN FY18: 50000; 5 YEAR CAPITAL PLAN FY21: 50000; 15 YEAR CAPITAL PLAN FY24: 50000; 15 YEAR CAPITAL PLAN FY27: 50000; 15 YEAR CAPITAL PLAN FY30: 50000
5062 | Various Building Improvements | Facilities/Town buildings | Facilities | 740000 | 150000 | Various | renovation/repair | D | FY15 | FY15-FY30 | 40000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  |  | 50000
| Consulting/Planning Services |  | Recreation | 50000 | [5 empty] | FY17
5090 | Schools classroom VCT Flooring Replacement | Facilities/SPS | SPS/Facilities | 500000 | -200000 | Multiple Schools | Flooring | B | FY15 | FY15-FY21 | 75000 | 100000 | 50000 | 50000 | 50000 | 75000 | 75000 |  | 75000 |  |  | 75000 |  |  | 75000 |  |  | 75000
| SPS and Town HVAC capital repairs | Facilities-LS | SPS/Facilities | 100000 | 45000 | LSRHS | Renovation | B |  | FY18-FY19 | 5 YEAR CAPITAL PLAN FY18: 55000
| poured in place surfacing for playground at Haskell |  | Recreation | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 71000
| Schools Playgrounds (Haynes, Loring, Nixon, Noyes) |  | SPS | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 150000; 5 YEAR CAPITAL PLAN FY19: 150000; 5 YEAR CAPITAL PLAN FY20: 150000; 5 YEAR CAPITAL PLAN FY21: 150000
5028 | School Maintenance Garage |  | SPS/Facilities | 100000 | [5 empty] | FY19 | 5 YEAR CAPITAL PLAN FY18: 95000
Library Teen Space Renovation | Library Teen Space Renovations |  | Library | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 200000
| Featherland tennis courts |  | Recreation | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 220000
| Cisco Meraki wireless infrastructure for the elementary schools |  | SPS | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 175000
5024 | Town and School Parking Lot(Loring and Fire Station) |  | DPW | 200000 | [5 empty] | FY16 | PAST PROJECTS FY15: 330000; PAST PROJECTS FY16: 200000; 5 YEAR CAPITAL PLAN FY18: 275000; 5 YEAR CAPITAL PLAN FY21: 250000; 15 YEAR CAPITAL PLAN FY27: 250000; 15 YEAR CAPITAL PLAN FY32: 250000
| Bruce Freeman Rail Trail Design/construction |  | Selectmen | 100000 | [5 empty] | FY19 | PAST PROJECTS FY17: CPC; 5 YEAR CAPITAL PLAN FY18: 330000
| Town Hall Restoration-Design Funds |  | Selectmen | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 600000
| Nixon School addition for SPS offices |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 4000000
| Fire Station 2 reconstruction |  | Fire | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 6000000
| Wayside Inn Preservation |  | Selectmen | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 6000000
| New Fairbank Community Center/Atkinson Pool Complex | Facilities/Town buildings | Selectmen | 16000000 | -4000000 | Fairbank | New Building | A |  | FY21-FY40 | 5 YEAR CAPITAL PLAN FY20: 20000000
5082 | DPW Cold Storage Addition | Facilities/Town buildings | DPW | 325000 | -57000 | DPW | Renovation | B |  | FY17 | 5 YEAR CAPITAL PLAN FY19: 382000; 5 YEAR CAPITAL PLAN FY20: 0
| Underground Fuel Storage Replacement | Facilities/Town buildings | DPW | 250000 | -550000 | DPW | renovation | B |  | FY16 | 5 YEAR CAPITAL PLAN FY19: 800000
5087 | Town-wide Drainage Upgrade Project | Facilities/Town buildings | DPW | 2000000 | -1000000 | Town wide | Infrastructure | A |  | FY26 | 5 YEAR CAPITAL PLAN FY22: 3000000
5089 | Sherman's Bridge Replacement | Other Town wide | DPW | 4000000 | 1847000 | Town wide | Infrastructure | A |  | FY21-FY40 | 5 YEAR CAPITAL PLAN FY20: 2153000
| Salt Shed fabric covering |  | DPW | [7 empty] | 5 YEAR CAPITAL PLAN FY21: 50000
5086 | Route 20 Intersections | Other Town wide | DPW | 250000 | 0 | None | Infrastructure | B |  | FY18-FY20 | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 250000; 5 YEAR CAPITAL PLAN FY21: 0
5095 | Library Roof Replacement (areas 4 & 5) | Facilities/Town buildings | Facilities | 143700 | 0 | Library | Roof Repair/Replacement | B |  | FY19 | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 143700
T | Town Hall Roof |  | Facilities | [7 empty] | 15 YEAR CAPITAL PLAN FY23: 800000
6018 | Atkinson Pool Roof and Façade Improvements | Enterprises | Facilities | 418000 | -200000 | Pool | Roof Repair/Replacement | B |  | FY16 | 5 YEAR CAPITAL PLAN FY19: 618000
5067 | DPW Highway Garage Roof | Facilities/Town buildings | Facilities | 124743 | 74743 | DPW | Roof Repair/Replacement | B |  | FY18 | PAST PROJECTS FY15: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY22: 50000
5157 | DPW Garage Floor Replacement | Facilities/Town buildings | Facilities | 150000 | 70000 | DPW | Renovation | B |  | FY18 | 5 YEAR CAPITAL PLAN FY22: 80000
5142 | Fairbank Center - Flat Roof | Facilities/Town buildings | Facilities | 700000 | -600000 | Fairbank | Roof Repair/Replacement | B |  | FY20 | 5 YEAR CAPITAL PLAN FY19: 1300000
1009 | Fairbank Window Replacement | Facilities/Town buildings | Facilities | 230000 | -500000 | Fairbank | Window Replacement | B |  | FY21 | 5 YEAR CAPITAL PLAN FY21: 730000
5132 | Fairbanks/Senior Center Fire Alarm/Sprinkler | Facilities/Town buildings | Facilities | 350000 | 0 | Fairbank | Fire Alarm/Sprinkler | B |  | FY18 | 5 YEAR CAPITAL PLAN FY22: 350000
5016 | Fire HQ Roof | Facilities/Town buildings | Facilities | 90295 | 0 | Fire Headquarters | Roof Repair/Replacement | B |  | FY18 | PAST PROJECTS FY15: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY20: 90295
5022 | Fire Station 3 Roof | Facilities/Town buildings | Facilities | 63430 | 0 | Fire Station 3 | Roof Repair/Replacement | B |  | FY17 | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY20: 63430
1011 | Flynn Building HVAC | Facilities/Town buildings | Facilities | 180000 | 0 | Flynn | HVAC | B |  | FY19 | 15 YEAR CAPITAL PLAN FY29: 180000
5038 | Library Roof Replacement (areas 2,3,6,7 and slate repairs) | Facilities/Town buildings | Facilities | 124379 | -621 | Library | Roof Repair/Replacement | B |  | FY18 | PAST PROJECTS FY15: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 125000
5037 | New Energy Management System for Library | Facilities/Town buildings | Facilities | 162000 | 0 | Library | Energy | B |  | FY17 | 5 YEAR CAPITAL PLAN FY22: 162000
5133 | ESCO (Energy Efficiency and Infrastructure Renewal) | Facilities/Town buildings | Facilities | 1838049 | 744976 | Various | Energy | B |  | FY15 | PAST PROJECTS FY15: 1093073
0 | Carding Mill House Roof | Facilities/Town buildings | Facilities | 19000 | 0 | Carding Mill House | Roof Repair/Replacement | D |  | FY20 | 5 YEAR CAPITAL PLAN FY22: 19000
6020 | South Fire Station Roof | Facilities/Town buildings | Facilities | 41057 | 0 | Fire Station 2 | Roof Repair/Replacement | D |  | FY18 | 5 YEAR CAPITAL PLAN FY21: 41057
6021 | Flynn Bldg. - 2nd floor bathroom | Facilities/Town buildings | Facilities | 30000 | 30000 | Flynn | Renovation | D |  | FY17
7042 | Flynn Building Roof Repair | Facilities/Town buildings | Facilities | 33746 | -254 | Flynn | Roof Repair/Replacement | D |  | FY17 | 5 YEAR CAPITAL PLAN FY21: 34000; 15 YEAR CAPITAL PLAN FY31: 95000
7045 | Hosmer House Roof | Facilities/Town buildings | Facilities | 36400 | 0 | Hosmer House | Roof Repair/Replacement | D |  | FY17 | 5 YEAR CAPITAL PLAN FY20: 36400
5154 | Town Hall - Clerk's Bathroom | Facilities/Town buildings | Facilities | 38000 | 0 | Town Hall | Renovation | D |  | FY20 | 5 YEAR CAPITAL PLAN FY20: 38000
5155 | Town Hall Bathrooms | Facilities/Town buildings | Facilities | 40000 | 0 | Town Hall | Renovation | D |  | FY20 | 5 YEAR CAPITAL PLAN FY20: 40000
5027 | Munis Software- Employee Self Service |  | Finance | 10425 | [5 empty] | FY16 | PAST PROJECTS FY16: 10425
5044 | Munis Software- Tyler Reporting Services |  | Finance | 22325 | [5 empty] | FY16 | PAST PROJECTS FY16: 22325
5041 | Self Contained Breathing Apparatus (SCBA) | Fire Equipment | Fire | 200000 | -50000 | None | Fire Apparatus | B |  | FY17 | PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY22: 250000
5034 | Cardiac Monitor Replacement |  | Fire | 96000 | [5 empty] | FY16 | PAST PROJECTS FY16: 96000
| New Breathing Air Compressor |  | Fire | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 75000
5032 | Radio Box Upgrades |  | Fire | 50000 | [5 empty] | FY16 | PAST PROJECTS FY16: 50000; PAST PROJECTS FY17: 50000
5040 | Fire HQ New Windows |  | Fire | 50000 | [5 empty] | FY18 | 5 YEAR CAPITAL PLAN FY20: 40000; 15 YEAR CAPITAL PLAN FY23: 80000
5004 | Fire Station 3 Rehab/Updates or reconstruction |  | Fire | 120000 | [5 empty] | FY19 | 15 YEAR CAPITAL PLAN FY29: 300000
5092 | Fire Station 2, install tight tanks |  | Fire | [7 empty] | 5 YEAR CAPITAL PLAN FY21: 60000
7036 | Fire HQ install tight tank |  | Fire | [7 empty] | PAST PROJECTS FY17: 50000
7010 | Fire HQ New Storage Building |  | Fire | 75000 | [5 empty] | FY20 | 5 YEAR CAPITAL PLAN FY20: 95000
7044 | Replace Complete Radio System |  | Fire | 1500000 | [5 empty] | FY22 | 5 YEAR CAPITAL PLAN FY20: 1500000
5152 | Town Technology Plan | Technology-Town | Info Systems | 500000 | 400000 | Various | Technology Planning | B |  | FY16-FY20 | PAST PROJECTS FY15: 0; 5 YEAR CAPITAL PLAN FY20: 100000
| LSRHS security upgrades |  | LSRHS | [7 empty] | PAST PROJECTS FY17: 128235; 15 YEAR CAPITAL PLAN FY24: 15000
| Hot water heater |  | LSRHS | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 65000
| Multi-Use Turf Fields |  | LSRHS |  |  | LSRHS |  |  |  |  | PAST PROJECTS FY17: 875000
5050 | LSRHS Roof Repair/Replacement | Facilities-LS | LSRHS | 1904000 | -1096000 | LSRHS | Roof Repair/Replacement | A |  | FY25-FY34 | 15 YEAR CAPITAL PLAN FY29: 3000000
| Gym 1 Bleachers |  | LSRHS | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 45000
| Gym 4 Floor replacement |  | LSRHS | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 40000
2004R | Boiler Building -Cold Storage Conversion | Facilities-LS | LSRHS | 200000 | 0 | LSRHS | Renovation | B |  | FY17 | 5 YEAR CAPITAL PLAN FY19: 200000
| Generators (2) | Facilities-LS | LSRHS | 250000 | 0 | LSRHS | Renovation | B |  | FY20 | 5 YEAR CAPITAL PLAN FY20: 250000
| Stadium Field Turf | Facilities-LS | LSRHS | 500000 | 0 | LSRHS | Renovation | B |  | FY20 | 5 YEAR CAPITAL PLAN FY19: 500000
| Elevators Replacement (2) | Facilities-LS | LSRHS | 220000 | 0 | LSRHS | Renovation | B |  | FY21 | 15 YEAR CAPITAL PLAN FY24: 220000
| Communication Clock System | Facilities-LS | LSRHS | 80000 | 0 | LSRHS | Renovation | B |  | FY23 | 5 YEAR CAPITAL PLAN FY22: 80000
| LSRHS Heat Pumps (319) | Facilities-LS | LSRHS | 1276000 | 0 | LSRHS | HVAC | B |  | FY24 | 15 YEAR CAPITAL PLAN FY24: 1276000
| Waste Water Treatment Facility |  | LSRHS
| Boiler Plant (2) | Facilities-LS | LSRHS | 300000 | 0 | LSRHS | Renovation | B |  | FY29 | 15 YEAR CAPITAL PLAN FY29: 300000
6002 | Expand Fitness Area and Replace Equipment | LS Equipment | LSRHS | 130000 | 0 | LSRHS | Equipment/Renovation | B |  | FY15 | 5 YEAR CAPITAL PLAN FY22: 130000
| Replace Aging Computers and Servers | Technology-LS | LSRHS | 120000 | -40000 | LSRHS | Technology | B | FY15 | FY15 | PAST PROJECTS FY15: 120000; 15 YEAR CAPITAL PLAN FY24: 40000
| Upgrade Technology - Network Infrastructure and WiFi Capacity | Technology-LS | LSRHS | 500000 | 0 | LSRHS | Technology | B | FY15 | FY15 | PAST PROJECTS FY15: 500000; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0
| Scheduled Replacement of Laptops, Student Labs, and Servers | Technology-LS | LSRHS | 320000 | 320000 | LSRHS | Technology | B |  | FY16
| Parking Lot (asphalt, sealing) | Facilities-LS | LSRHS | 30000 | -90000 | LSRHS | Renovation | D |  | FY25 | 5 YEAR CAPITAL PLAN FY19: 40000; 5 YEAR CAPITAL PLAN FY20: 40000; 5 YEAR CAPITAL PLAN FY21: 40000; 15 YEAR CAPITAL PLAN FY30: 300000
| Phone System upgrades | LS Equipment | LSRHS | 35000 | -35000 | LSRHS | Equipment | D |  | FY17 | 5 YEAR CAPITAL PLAN FY20: 70000
Cooling Towers | Cooling Towers/major maintenance |  | LSRHS | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 110000
| Fire Alarm System Upgrading |  | LSRHS | 125000 | [5 empty] | FY16 | PAST PROJECTS FY16: 125000
| HVAC Controls/Heat Pumps |  | LSRHS
| Mass Central Rail Trail Phase 1 |  | Planning | 160000 | [5 empty] | FY16 | 5 YEAR CAPITAL PLAN FY20: 160000
| Mass Central Rail Trail Phase 2 |  | Planning | 450000 | [6 empty] | 15 YEAR CAPITAL PLAN FY27: 450000
| Route 20 Sewer |  | Planning | 15000000 | [5 empty] | FY17 | 5 YEAR CAPITAL PLAN FY21: 15000000
| Johnson Farm Purchase |  | Planning | 3700000 | [5 empty] | FY16 | PAST PROJECTS FY16: 3700000
| Purchase of Land 36 North Road |  | Planning | 457100 | [5 empty] | FY16 | 5 YEAR CAPITAL PLAN FY19: 457100
| CSX Rail Corridor Purchase |  | Planning | 750000 | [5 empty] | FY17 | 5 YEAR CAPITAL PLAN FY19: 750000
| New Dispatch Technology/equipment |  | Police
| Feeley Field Reconstruction | Recreation | Recreation | 1815000 | 0 | Recreation Fields | Rec Field Construct./Devel. | A |  | FY16-FY35 | 5 YEAR CAPITAL PLAN FY20: 1815000
| Family changing room at the pool/locker room renovations | Enterprises | Recreation | 100000 | -200000 | Fairbank | Renovation | B |  | FY22 | 5 YEAR CAPITAL PLAN FY19: 300000
| Construct a zero entry warm water pool and spray ground | Facilities/Town buildings | Recreation | 500000 | 0 | Fairbank | new addition | B |  | FY22 | 15 YEAR CAPITAL PLAN FY25: 500000
| Field Development (Davis, Featherland, Ti-Sales property) | Recreation | Recreation | 1865000 | 0 | Recreation Fields | Rec Field Construct/Devel. | B |  | FY16 | 5 YEAR CAPITAL PLAN FY19: 1865000
| Haskell Complex Redevelopment (FY20) | Recreation | Recreation | 200000 | 0 | Recreation Fields | Rec Field Construct./Devel. | B |  | FY20 | 5 YEAR CAPITAL PLAN FY20: 200000; 5 YEAR CAPITAL PLAN FY21: 0
| Haskell Playground Upgrades (FY20) | Recreation | Recreation | 100000 | 0 | Recreation Fields | Rec Field Construct./Devel. | B |  | FY20 | 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 100000
| Feeley Tennis Courts |  | Recreation | 40000 | [5 empty] | FY16 | PAST PROJECTS FY16: 40000
| Lighting Cutting Field |  | Recreation | 275000 | [5 empty] | FY16 | 5 YEAR CAPITAL PLAN FY19: 300000
| Davis Field Development |  | Recreation | 3573512 | [5 empty] | FY16 | 15 YEAR CAPITAL PLAN FY23: 500000
| Haskell Pavilion Construction |  | Recreation | 60000 | [5 empty] | FY19 | 5 YEAR CAPITAL PLAN FY19: 60000
| Improve Feeley Softball/Add Lighting |  | Recreation | 450000 | [5 empty] | FY17 | 5 YEAR CAPITAL PLAN FY22: 450000
| Replace Cutting Turf Field |  | Recreation | 450000 | [5 empty] | FY20 | 5 YEAR CAPITAL PLAN FY19: 450000
| Install a Spray ground at Haskell Field |  | Recreation | 250000 | [5 empty] | FY23 | 15 YEAR CAPITAL PLAN FY23: 250000
| Lighting Turf 1 and Turf 2 |  | Recreation | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 400000; 15 YEAR CAPITAL PLAN FY25: 30000
5063 | Melone Redevelopment Study |  | Selectmen | 160000 | [5 empty] | FY17 | 5 YEAR CAPITAL PLAN FY19: 160000
| Loring Parsonage Restoration-Museum |  | Selectmen | [7 empty] | PAST PROJECTS FY17: 400000
5064 | Nobscot Road/Union Ave Extension |  | Selectmen | [7 empty] | 15 YEAR CAPITAL PLAN FY26: 1000000
| Construct Police Station | Facilities/Town buildings | Selectmen | 8527000 | 327000 | Police Station | New Building | A | FY15 | FY16-FY35 | PAST PROJECTS FY15: 8200000
| Town Hall Renovations | Facilities/Town buildings | Selectmen | 9000000 | 3000000 | Town Offices | New Building | A |  | FY20-FY39 | 5 YEAR CAPITAL PLAN FY20: 6000000
| School Phone Sys comp w/town (4 schools: Curtis, Noyes, Loring & Haynes) | Facilities/SPS | SPS | 150000 | 58000 | Multiple Schools | Technology Planning | B | FY15 | FY15-FY19 | PAST PROJECTS FY15: 40000; PAST PROJECTS FY16: 25000; PAST PROJECTS FY17: 27000
| SPS Technology Plan | Technology-SPS | SPS | 570000 | 400000 | Various | Technology Planning | B | FY15 | FY15-FY20 | PAST PROJECTS FY15: 70000; 5 YEAR CAPITAL PLAN FY20: 100000
| Curtis School A/C rooftop unit replacement |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY20: 75000
5025 | School Security and Access Controls |  | SPS/Facilities | 500000 | [5 empty] | FY16 | PAST PROJECTS FY16: 220000; PAST PROJECTS FY17: 95000; 5 YEAR CAPITAL PLAN FY20: 95000; 5 YEAR CAPITAL PLAN FY22: 100000; 15 YEAR CAPITAL PLAN FY26: 50000; 15 YEAR CAPITAL PLAN FY28: 50000; 15 YEAR CAPITAL PLAN FY31: 50000
5101 | Emergency Generators at all schools | Facilities/SPS | SPS/Facilities | 100000 | 0 | Curtis School | Electrical Work | B |  | FY20 | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 100000
2005 | Nixon Roof Areas 1,2,4,5,6 | Facilities/SPS | SPS/Facilities | 1000000 | -200000 | Nixon School | Roof Repair/Replacement | A |  | FY20 | 5 YEAR CAPITAL PLAN FY21: 1200000
1001 | Curtis Middle School Roof Replacement | Facilities/SPS | SPS/Facilities | 2100000 | 2100000 | Curtis School | Roof Repair/Replacement | A |  | FY21-FY30 | 15 YEAR CAPITAL PLAN FY30: 2500000
1002 | Haynes Roof Areas 5,6,7,9 | Facilities/SPS | SPS/Facilities | 1000000 | 0 | Haynes School | Roof Repair/Replacement | A |  | FY17 | 5 YEAR CAPITAL PLAN FY20: 1000000
1010 | Haynes Roof Areas 2,3,4,8,10 | Facilities/SPS | SPS/Facilities | 1000000 |  | Haynes School | Roof Repair/Replacement |  |  | FY21 | 5 YEAR CAPITAL PLAN FY21: 1000000
7038 | Loring School Roof Replacement | Facilities/SPS | SPS/Facilities | 1155000 | 242 | Loring School | Roof Repair/Replacement | A |  | FY22-FY31 | 5 YEAR CAPITAL PLAN FY21: 1154758
5153 | Curtis School RTU HVAC #7 | Facilities/SPS | SPS/Facilities | 70000 | 0 | Curtis School | HVAC | B |  | FY17 | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY20: 70000
5014 | Curtis School RTU HVAC #8 | Facilities/SPS | SPS/Facilities | 70000 | 0 | Curtis School | HVAC | B |  | FY17 | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY19: 70000
5100 | Curtis School RTU HVAC #9, #12 | Facilities/SPS | SPS/Facilities | 105000 | 0 | Curtis School | HVAC | B |  | FY18 | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY22: 105000
5099 | New Energy Management System for Curtis | Facilities/SPS | SPS/Facilities | 230000 | 230000 | Curtis School | Energy | B |  | FY19
5110 | Loring boiler control | Facilities/SPS | SPS/Facilities | 100000 | 25000 | Loring School | HVAC | B |  | FY16 | PAST PROJECTS FY17: 0; 15 YEAR CAPITAL PLAN FY23: 75000
5097 | Nixon Cafetorium Roof/windows and exterior doors | Facilities/SPS | SPS/Facilities | 400000 | -696268 | Nixon School | repair/replacement | B |  | FY15 | PAST PROJECTS FY16: 1096268
5107 | Nixon Fire Sprinkler | Facilities/SPS | SPS/Facilities | 400000 | 400000 | Nixon School | Sprinkler | B |  | FY17 | 5 YEAR CAPITAL PLAN FY21: 0
5146 | Noyes Fire Sprinkler System | Facilities/SPS | SPS/Facilities | 490000 | 0 | Noyes School | Fire Alarm/Sprinkler | B |  | FY18 | 5 YEAR CAPITAL PLAN FY21: 490000
5145 | Generator Replacement - Noyes | Facilities/SPS | SPS/Facilities | 85000 | 0 | Noyes School | Electrical Work | B |  | FY19 | 15 YEAR CAPITAL PLAN FY23: 85000
5129 | Curtis Univent for Room 148 Replacement | Facilities/SPS | SPS/Facilities | 12000 | 0 | Curtis School | Renovation | D |  | FY20 | 5 YEAR CAPITAL PLAN FY20: 12000
| Curtis Water Heater | Facilities/SPS | SPS/Facilities | 25000 | 0 | Curtis School | HVAC | D |  | FY20 | 15 YEAR CAPITAL PLAN FY29: 25000
7026 | Noyes Septic System Replacement | Facilities/SPS | SPS/Facilities | 400000 | 400000 | Noyes School | Town wide Facilities Planning/Design | D |  | FY20 | 15 YEAR CAPITAL PLAN FY31: 200000
5058 | Curtis School Septic Pumps |  | SPS/Facilities | 40000 | 0 | Curtis School |  |  |  | FY16
5056 | Haynes School Septic Pump |  | SPS/Facilities | 40000 | 0 | Haynes School |  |  |  | FY16 | PAST PROJECTS FY16: 40000; 5 YEAR CAPITAL PLAN FY21: 40000; 5 YEAR CAPITAL PLAN FY22: 150000
5053 | Noyes Wood Siding Replacement on Art Room |  | SPS/Facilities | 15000 | [5 empty] | FY17 | 5 YEAR CAPITAL PLAN FY20: 15000
5061 | Noyes Elevator Replacement |  | SPS/Facilities | 150000 | [5 empty] | FY18 | 15 YEAR CAPITAL PLAN FY31: 400000
5060 | Noyes Electrical Feeder and Remote Subpanel Replacement |  | SPS/Facilities | 250000 | [5 empty] | FY21 | 5 YEAR CAPITAL PLAN FY22: 80000
| Painting Interior |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY20: 30000
| Sand and refinish Gymnasium floor |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 12000; 5 YEAR CAPITAL PLAN FY21: 14000; 15 YEAR CAPITAL PLAN FY23: 15000; 15 YEAR CAPITAL PLAN FY25: 15000; 15 YEAR CAPITAL PLAN FY27: 15000
5066 | Traffic Lights at Nixon School Crossing |  | SPS/Facilities | 75000 | [5 empty] | FY17 | PAST PROJECTS FY17: 25000
5039 | Noyes Rooftop HVAC Replacement |  | SPS/Facilities | 100000 | [5 empty] | FY19
5096 | Noyes Envelope Repointing and Caulking |  | SPS/Facilities | 300000 | [5 empty] | FY20
5042 | Nixon Hot Water Heater Replacement |  | SPS/Facilities | 25000 | [5 empty] | FY16 | PAST PROJECTS FY16: 25000; 5 YEAR CAPITAL PLAN FY22: 400000; 15 YEAR CAPITAL PLAN FY23: 250000
5043 | Nixon Rooftop HVAC Replacement, library and Gym |  | SPS/Facilities | 200000 | [5 empty] | FY17 | 5 YEAR CAPITAL PLAN FY20: 100000
5029 | Nixon Switchgear and Feeder Rewiring replacement |  | SPS/Facilities | 400000 | [5 empty] | FY21 | 5 YEAR CAPITAL PLAN FY22: 50000
5031 | Various Exterior&interior Door Repair/Replacement at all Schools |  | SPS/Facilities | 50000 | [5 empty] | FY17 | PAST PROJECTS FY16: 40000
5020 | Haynes Rooftop HVAC Replacements |  | SPS/Facilities | 150000 | [5 empty] | FY18 | 5 YEAR CAPITAL PLAN FY20: 75000; 5 YEAR CAPITAL PLAN FY22: 95000; 15 YEAR CAPITAL PLAN FY25: 50000
5036 | School Rooftop HVAC Unit (Noyes and Loring) |  | SPS/Facilities | 75000 | [5 empty] | FY16 | PAST PROJECTS FY16: 75000; PAST PROJECTS FY17: 75000
| Walk-in Refrigerators at Schools |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY21: 45000
| Loring Fire Alarm System upgrade |  | SPS/Facilities | 30000 | [6 empty] | 15 YEAR CAPITAL PLAN FY23: 30000
School Custodial Equipment | School Custodial Equipment |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 34000; 5 YEAR CAPITAL PLAN FY21: 34000
| Noyes Fire Alarm System Replacement |  | SPS/Facilities | 100000 | [6 empty] | 15 YEAR CAPITAL PLAN FY24: 100000
| New Voting Boxes |  | Town Clerk | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 48000
| Large Projects- above the expected annual capital | [9 empty] | -9293073 | -4796268 |  | -6000000 | -13165000 | -32468000 | -18354758 | -3000000 |  | -1276000 |  | -1000000 |  |  | -3000000 | -2500000
| TOTAL CAPITAL |  |  | 99471161 | 1846628 |  |  |  |  | 26194157 | 1275000 | 1326750 | 1875235 | 2468190 | 6166100 | 2685125 | 2396757 | 2651000 | 2210000 | 525000 | 745000 | 175000 | 765000 | 50000 | 880000 | 400000 | 795000 | 325000
73277004
| ROLLING STOCK | [9 empty] | PAST PROJECTS FY15: PAST PROJECTS; 5 YEAR CAPITAL PLAN FY18: 5 YEAR CAPITAL PLAN; 15 YEAR CAPITAL PLAN FY23: 15 YEAR CAPITAL PLAN
3028 | 2009 Utility Trailer T1 | Ce | Cemetery
3077 | 2002 Big Utility Trailer T12 |  | Cemetery
3071 | 2002 Giant Trailer T14 |  | Cemetery
3069 | *2015 Chevy Silverado 3/4 Ton unit 1 |  | DPW |  |  | 1 |  |  |  |  | PAST PROJECTS FY15: 38030; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 45000
3021 | *2015 Chevy Silverado Pick-Up unit 2 |  | DPW |  |  | 2 |  |  |  |  | PAST PROJECTS FY15: 35405; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 45000
3083 | *2007 Mack 6-Whl Dump Truck unit 3 |  | DPW |  |  | 3 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY27: 150000
3074 | *2013 Freightliner 6-Whl Dump Truck - New in FY13 Unit 4 |  | DPW |  |  | 4 |  |  |  |  | 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 127000; 15 YEAR CAPITAL PLAN FY31: 137000
3038 | *2008 Volvo 10 Wheel Dump Truck unit 5 |  | DPW |  |  | 5 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 160000; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY32: 160000
3025 | *2006 Mack Ten Wheeler Dump Truck unit 6 |  | DPW |  |  | 6 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 5 YEAR CAPITAL PLAN FY22: 160000
3030 | 2015 Chevy Silverado 1 Ton unit 7 |  | DPW |  |  | 7 |  |  |  |  | PAST PROJECTS FY15: 49829; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY26: 48000
3040 | 2009 John Deere 544K Loader unit 8 |  | DPW |  |  | 8 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 208000
| *2016 6 Wheel Dump Truck unit 9 |  | DPW |  |  | 9 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 170230; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 145000
3034 | *2012 Freightliner 10-Wheel Dump unit 10 |  | DPW |  |  | 10 |  |  |  |  | PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY23: 165000
3080 | *2014 Mack Dump 6-Wheel (leased in fy14) unit 11 |  | DPW |  |  | 11 |  |  |  |  | 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 165000
3017 | *2006 Mack 10-Wheel Dump unit 12 |  | DPW |  |  | 12 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY28: 134000
3091 | *2008 Chevy Silverado Flat Bed unit 13 |  | DPW |  |  | 13 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 48000; 15 YEAR CAPITAL PLAN FY28: 48000
3011 | *2009 Chevy Pick-Up unit 14 |  | DPW |  |  | 14 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 45000; 5 YEAR CAPITAL PLAN FY21: 0
3039 | 2014 Loader unit 15 |  | DPW |  |  | 15 |  |  |  |  | PAST PROJECTS FY15: 154000; 15 YEAR CAPITAL PLAN FY30: 154000
3024 | 2014 John Deere Backhoe unit 16 |  | DPW |  |  | 16 |  |  |  |  | 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY29: 30000
3078 | *2015 Chevy Pick Up unit 17 |  | DPW |  |  | 17 |  |  |  |  | PAST PROJECTS FY15: 40724; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 45000
3092 | *2007 Mack 6 Wheel Dump Truck unit 18 |  | DPW |  |  | 18 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY27: 150000
3079 | 2015 Freightliner 6 Wheel Dump unit 19 |  | DPW |  |  | 19 |  |  |  |  | 5 YEAR CAPITAL PLAN FY20: 24000; 5 YEAR CAPITAL PLAN FY21: 0
3075 | *2011 Volvo 6 Wheel Dump Truck unit 20 |  | DPW |  |  | 20 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY23: 155000
3016 | 2012 Prinoth Multi-Purpose Tractor unit 21 |  | DPW |  |  | 21 |  |  |  |  | 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY26: 165000
3009 | 2009 John Deere Backhoe/Loader unit 22 |  | DPW |  |  | 22 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 145000
3027 | *2008 International 6-Wheel Dump unit 23 |  | DPW |  |  | 23 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY28: 150000
3035 | *2008 International 4x4 Truck unit 24 |  | DPW |  |  | 24 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY28: 150000
3076 | 2005 Komatsu Backhoe unit 25 |  | DPW |  |  | 25 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 135000; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY30: 135000
3023 | 2009 Bobcat unit 26 |  | DPW |  |  | 26 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 55000
| *2007 Mack 10-Whl Dump Truck unit 27 |  | DPW |  |  | 27 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY27: 165000
3020 | *2015 Chevy Silverado 1 Ton Unit 28 |  | DPW |  |  | 28 |  |  |  |  | PAST PROJECTS FY15: 55869; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY28: 55000
| *2013 Chevy 1 Ton Dump Truck Unit 29 |  | DPW |  |  | 29 |  |  |  |  | PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 5 YEAR CAPITAL PLAN FY22: 50000
3029 | 2005 4x4 pickup truck Unit #30 |  | DPW
3036 | 2014 Bandit Chipper unit #31 |  | DPW |  |  | 31 |  |  |  |  | PAST PROJECTS FY15: 40748; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 56000
3024 | 1987 Air compressor Unit 32 |  | DPW
3026 | 2013 Prinoth sidewalk Tractor unit 33 (141,000) |  | DPW |  |  | 33 |  |  |  |  | 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 28000; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY31: 28000
3037 | 2016 Freightliner unit 34 (183,000) |  | DPW |  |  | 34 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 133395; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY26: 134000; 15 YEAR CAPITAL PLAN FY31: 133395
3015 | 2010 Kubota Tractor/Boom Flail Mower unit 35 |  | DPW |  |  | 35 |  |  |  |  | PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY26: 95000
| *2000 GMC - swap body unit 36 |  | DPW |  |  | 36 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 140000; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 50000
3081 | *2011 Chevy 1 Ton 6 Wheel Dump unit 37 |  | DPW |  |  | 37 |  |  |  |  | PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 55000; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY28: 55000
3008 | *2015 Chevy Silverado - 1 Ton unit 38 |  | DPW |  |  | 38 |  |  |  |  | PAST PROJECTS FY15: 57745; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY23: 55000
| 2002 air compressor unit # 39 |  | DPW
| *2015 Chevy 1 Ton P/U unit 40 |  | DPW |  |  | 40 |  |  |  |  | PAST PROJECTS FY15: 57445; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 45000
3032 | 2016 case Loader or Equivalent unit 41 |  | DPW |  |  | 41 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 50000; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY31: 55000
3033 | 2016 Sidewalk Roller Unit # 42 |  | DPW | [7 empty] | PAST PROJECTS FY17: 31000
3010 | 1990 cement mixer Unit #43 |  | DPW
| *2004 Mack 6 Wheel Dump Truck unit 44 |  | DPW |  |  | 44 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 145000
| *2015 GM 2400 Utility Truck unit 45 |  | DPW |  |  | 45 |  |  |  |  | PAST PROJECTS FY15: 36321; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0
3067 | 2005 Multi-Purpose Holder unit 46 |  | DPW |  |  | 46 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY18: 182000; 5 YEAR CAPITAL PLAN FY20: 0; 15 YEAR CAPITAL PLAN FY28: 190000
3073 | 2017 purchase new Loader |  | DPW | [7 empty] | PAST PROJECTS FY17: 210000; 15 YEAR CAPITAL PLAN FY29: 203000
| 2007 Mower attachment Unit 47 |  | DPW
| 2004 Volvo L90E Loader unit 48 |  | DPW |  |  | 48 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0
| 2004 Bandit Chipper unit 49 |  | DPW |  |  | 49 |  |  |  |  | PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 40000; 15 YEAR CAPITAL PLAN FY30: 50000
3070 | Sidewalk Paver unit # 50 |  | DPW | [7 empty] | 5 YEAR CAPITAL PLAN FY21: 41000; 15 YEAR CAPITAL PLAN FY28: 50000
3022 | 2008 Air Compressor unit 51 |  | DPW
3084 | 2005 traffic utility trailer unit 52 |  | DPW
| 2009 M-B Tractor unit 53 |  | DPW |  |  | 53 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 140000
3007 | 2010 Elgin Pelican Sweeper unit 54 |  | DPW |  |  | 54 |  |  |  |  | PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 33236; 15 YEAR CAPITAL PLAN FY29: 175000
3049 | 10-foot Stainless Steel Sander (2015) |  | DPW |  |  | 55-ACC |  |  |  |  | PAST PROJECTS FY15: 19300; 15 YEAR CAPITAL PLAN FY26: 20000
3068 | New Excavator |  | DPW | [7 empty] | 5 YEAR CAPITAL PLAN FY22: 180000
3060 | 11-foot Hydraulic Plow (2015) |  | DPW |  |  | 56-ACC |  |  |  |  | PAST PROJECTS FY15: 12500; 15 YEAR CAPITAL PLAN FY26: 15000
| 2012 Carma Utility Trailer T5 |  | DPW
3048 | 2012 Kaufman Utility Trailer T6 |  | DPW
3051 | 2016 CAM Utility Trailer T7 |  | DPW
3082 | 2002 CAM Utility Trailer T11 |  | DPW
3044 | 2015 Ambulance F1 (9 year cycle) |  | Fire |  |  | A-1 |  |  |  |  | PAST PROJECTS FY15: 220000; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY24: 250000
3050 | Ambulance F2 |  | Fire |  |  | A-2 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 265000; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY28: 260000
3072 | New Ambulance F3 |  | Fire |  |  | A-3 |  |  |  |  | 5 YEAR CAPITAL PLAN FY19: 265000; 15 YEAR CAPITAL PLAN FY30: 265000
3052 | Bucket Truck (Fire Dept.) |  | Fire |  |  | B-1 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY18: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 125000
3060a | Car (Fire Dept.) |  | Fire |  |  | C-1 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY18: 40000; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY23: 40000; 15 YEAR CAPITAL PLAN FY28: 40000
| Car (Fire Dept.) |  | Fire |  |  | C-2 |  |  |  |  | PAST PROJECTS FY15: 40000; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 40000; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 40000; 15 YEAR CAPITAL PLAN FY30: 40000
3062 | Car 3 (Fire Dept.) |  | Fire |  |  | C-3 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 46000; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 5 YEAR CAPITAL PLAN FY22: 45000; 15 YEAR CAPITAL PLAN FY27: 45000; 15 YEAR CAPITAL PLAN FY32: 45000
| 2015 Fire Engine 1 |  | Fire |  |  | E-1 |  |  |  |  | PAST PROJECTS FY15: 465000; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY32: 465000
| Fire Engine 2 |  | Fire |  |  | E-2 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY27: 550000
| Fire Engine 3 |  | Fire |  |  | E-3 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY29: 555000
3002 | Fire Engine 4 |  | Fire |  |  | E-4 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; 5 YEAR CAPITAL PLAN FY19: 525000; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0
3001 | 2001 Pickup Truck (Fire Dept.) Eng 8 |  | Fire |  |  | FT1 |  |  |  |  | 5 YEAR CAPITAL PLAN FY21: 45000; 15 YEAR CAPITAL PLAN FY31: 55000
7001 | 2005 Pickup Truck (Fire Dept.) Eng 7 |  | Fire |  |  | FT2 |  |  |  |  | 15 YEAR CAPITAL PLAN FY25: 45000
3056 | 2008 Chevy 1-ton Pickup (Fire Dept.) M-1 |  | Fire |  |  | FT3 |  |  |  |  | 15 YEAR CAPITAL PLAN FY28: 45000
7001a | Ladder Truck |  | Fire |  |  | L-1 |  |  |  |  | PAST PROJECTS FY15: 0; 5 YEAR CAPITAL PLAN FY18: 995000; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0
7001b | Athletic Van - 2009-Chevrolet Express Van- 15 Passenger |  | LSRHS | [7 empty] | 5 YEAR CAPITAL PLAN FY19: 45000; 15 YEAR CAPITAL PLAN FY29: 55000
| Athletic Van - 2014-Chevrolet Express Van- 15 Passenger |  | LSRHS |  |  | LAV3 |  |  |  |  | 15 YEAR CAPITAL PLAN FY24: 45000
| Athletic Van - 2011-Chevrolet Express Van- 15 Passenger |  | LSRHS |  |  | LAV4 |  |  |  |  | 5 YEAR CAPITAL PLAN FY21: 45000; 15 YEAR CAPITAL PLAN FY31: 50000
| Athletic Van - 2013 Chevrolet Express Van-15 Passenger |  | LSRHS |  |  | LAV5 |  |  |  |  | 15 YEAR CAPITAL PLAN FY23: 45000
| Buildings & Grounds -2015 Ford F450 Dump Truck |  | LSRHS |  |  | LB1 |  |  |  |  | 15 YEAR CAPITAL PLAN FY25: 50500
| Buildings & Grounds 2010 Ford F350 Pickup Truck/sander |  | LSRHS |  |  | LB2 |  |  |  |  | 5 YEAR CAPITAL PLAN FY20: 40000; 15 YEAR CAPITAL PLAN FY30: 40000
| Buildings & Grounds -2012 Ford F350 Pickup Truck |  | LSRHS |  |  | LB4 |  |  |  |  | 5 YEAR CAPITAL PLAN FY22: 50500; 15 YEAR CAPITAL PLAN FY32: 55000
7001c | Gehl Skid Steer (currently 2006) |  | LSRHS | [7 empty] | 15 YEAR CAPITAL PLAN FY26: 25000
7001d | Aerila Fork Lift (currently 2004) |  | LSRHS | [7 empty] | 15 YEAR CAPITAL PLAN FY27: 27000
7003b | Kubota Front End Loader (currently 2002) |  | LSRHS | [7 empty] | 5 YEAR CAPITAL PLAN FY21: 35000
7002 | Smith Co. Super Rake (currently 2016) |  | LSRHS | [7 empty] | 15 YEAR CAPITAL PLAN FY31: 18000
3087 | 60 inch Mower (currently 2007) |  | LSRHS
7003a | 72 inch Mower (currently 2013) |  | LSRHS | [7 empty] | 15 YEAR CAPITAL PLAN FY32: 17000
3085 | Student Services Van - 2013 Chevrolet Express Van -15 Passenger |  | LSRHS |  |  | LS1 |  |  |  |  | 15 YEAR CAPITAL PLAN FY23: 45000
| *2015 Chevy Six Wheel Pickup unit# PR-1 |  | Parks & Gnds |  |  | PR-1 |  |  |  |  | PAST PROJECTS FY15: 34082; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 45000
| *2016 Chevy 1-Ton Pick-Up Truck unit # PR-11 |  | Parks & Gnds |  |  | PR-11 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 42645; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY26: 45000
| 2003 John Deere Tractor |  | Parks & Gnds |  |  | PR-15 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 5 YEAR CAPITAL PLAN FY22: 45000
| *2011 Chevrolet 6 Wheel Dump unit PR-2, leased in 2012 |  | Parks & Gnds |  |  | PR-2 |  |  |  |  | PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 5 YEAR CAPITAL PLAN FY22: 55000; 15 YEAR CAPITAL PLAN FY32: 65000
| *2015 Chevrolet 1-Ton Pick-Up unit # PR-3 |  | Parks & Gnds |  |  | PR-3 |  |  |  |  | PAST PROJECTS FY15: 42671; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 55000
| *2016 Chevy One Ton Pick-Up Truck-unit # PR-4 |  | Parks & Gnds |  |  | PR-4 |  |  |  |  | PAST PROJECTS FY16: 41054; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 15 YEAR CAPITAL PLAN FY25: 45000
| 2011 Big Tex Utility Trailer PR5 | Parks & Gnds | Parks & Gnds
| 2014 Toro Groundmaster PR7 |  | Parks & Gnds
| 2014 Big Tex Utility Trailer PR8 |  | Parks & Gnds
| 2001 Giant-Vac Trailer PR10 |  | Parks & Gnds
| 2014 Big Tex Trailer T4 |  | Parks & Gnds
| 2016 CAM Utility Trailer T15 |  | Parks & Gnds
| Storage Container |  | Parks & Gnds
| 2007 Super Z Mower #1 (12,000) |  | Parks & Gnds
| 2007 Super Z Mower #2 (12,000) |  | Parks & Gnds
| 2011 Super Z Mower #3 (12,000) |  | Parks & Gnds
| 2012 Super Z Mower #4 (12,000) |  | Parks & Gnds
| 1989 Toro Sand Pro infield machine (22,000) |  | Parks & Gnds
| 2006 Toro Sand Pro infield machine (22,000) |  | Parks & Gnds
| 2010 John Deere Tractor |  | Parks & Gnds |  |  | PR-6 |  |  |  |  | PAST PROJECTS FY15: 0; PAST PROJECTS FY16: 0; PAST PROJECTS FY17: 0; 5 YEAR CAPITAL PLAN FY19: 0; 5 YEAR CAPITAL PLAN FY20: 0; 5 YEAR CAPITAL PLAN FY21: 0; 5 YEAR CAPITAL PLAN FY22: 110000
| 1999 Chevy One ton Diesel Truck w/ Lift gate & Plow |  | SPS |  |  | ST1 |  |  |  |  | 5 YEAR CAPITAL PLAN FY18: 50000; 15 YEAR CAPITAL PLAN FY28: 50000
3090 | 2006 7-Passenger Van #2 |  | SPS |  |  | SV2 |  |  |  |  | 5 YEAR CAPITAL PLAN FY20: 30000; 15 YEAR CAPITAL PLAN FY27: 30000
7039 | 1997 Bobcat 763H |  | SPS | [7 empty] | 15 YEAR CAPITAL PLAN FY31: 48000
7041 | 2016 Cam Tilt Trailer |  | SPS | [7 empty] | 15 YEAR CAPITAL PLAN FY26: 4200
| 2006 Ford E-150 School Van |  | SPS | [7 empty] | 15 YEAR CAPITAL PLAN FY25: 22000
| 1998 Ford E-250 School Van HP |  | SPS | [7 empty] | 5 YEAR CAPITAL PLAN FY22: 34500; 15 YEAR CAPITAL PLAN FY32: 35000
| 2013 Big Tex Utility Trailer |  | SPS | [7 empty] | 15 YEAR CAPITAL PLAN FY23: 4000
| 2001 Chevy 1-Ton Flatbed |  | SPS | [7 empty] | 5 YEAR CAPITAL PLAN FY22: 45000
| 2002 Chevy 1 Ton Flatbed |  | SPS | [7 empty] | 15 YEAR CAPITAL PLAN FY23: 5000
| 2014 Bravo Trailer |  | SPS | [7 empty] | 15 YEAR CAPITAL PLAN FY24: 9000
| 2015 Cam Dump Trailer |  | SPS | [7 empty] | 15 YEAR CAPITAL PLAN FY25: 5800
| Purchase new work van for electrician |  | SPS/Facilities | [7 empty] | 5 YEAR CAPITAL PLAN FY18: 26000; 15 YEAR CAPITAL PLAN FY30: 26000
| 2016 Mack 10 Wheel Roll-Off (Transfer Stn) |  | Transfer Sta |  |  | L-1 |  |  |  |  | PAST PROJECTS FY16: 181540; 15 YEAR CAPITAL PLAN FY31: 191540
| 2016 CAM Utility Trailer T9 |  | Transfer Sta
| Building Dept. Electric Vehicle |  | Building | [7 empty] | 15 YEAR CAPITAL PLAN FY32: 38000
| Larger Vehicles | [9 empty] | 5 YEAR CAPITAL PLAN FY18: -995000; 5 YEAR CAPITAL PLAN FY19: -525000; 15 YEAR CAPITAL PLAN FY27: -550000
| TOTAL ROLLING STOCK | [9 empty] | 1399669 | 568864 | 602000 | 298000 | 450000 | 557000 | 414236 | 775000 | 514000 | 1054000 | 972300 | 551200 | 567000 | 1227000 | 1018000 | 710000 | 715935 | 880000