## status
TOWN OF SUDBURY COMMUNITY PRESERVATION ACT PROJECTS AS OF April 12, 2007
Year | total # projects | 3% Tax Surcharge | State Match | Total | Name of Project | $ Appropriated | Open space |  | Recreation |  | Historic Preservation |  | Community Housing |  | Article | Project Description |  | Project Status |  | Terms-deadline
2002 (FY03) | 0 | 1019875 | no match | 1019875 | Act adopted, no projects submitted
2003 (FY04) | 3 | 1085238 | 1030840 | 2116078 | Purchase of Dickson Land | 430000 | 391600 | 64% |  |  | 38400 | 36% |  |  | Article 32B $104,975 from FY04 (reflects debt service for bonds/notes over a 5-year term) | Acquisition of 2.39 acre parcel |  | Completed | Copy of Deed on file
[5 empty] | Hosmer House Restoration | 51600 |  |  |  |  | 51600 | 100% |  |  | Article 32A Appropriated from CPF revenue FY04 | Rehabilitation and restoration of building exterior and interior including a survey of conditions, installation of a climate control system, security upgrades and replacements |  | Completed | Survey completed and on file
[5 empty] | Community Rental Housing | 320000 | [6 empty] | 320000 | 100% | Article 32C Money transferred to SHA from FY04 CPF revenues | Construction of homes for 16 families in 7 houses |  | money given back | The Sudbury Housing Authority voted on 11/18/05 to close down its project and return $320,000.
| Total Appropriated funds 2003 |  |  |  |  | 801600 | 391600 |  | 0 |  | 90000 |  | 320000
2004 (FY05) | 3 | 1108053 | 1090772 | 2198825 | Cutting Farm | 5318500 | 4718500 | 89% | 600000 | 11% |  |  |  |  | Article 25 appropriate $530,000 from CPF revenues & reserves FY05 to pay debt service | Purchase of development rights through an APR on 55 acres; Purchase of 4 acres for active recreation field; bonded for 20-years |  | Completed | APR on file
[5 empty] | Revolutionary War Cemetery | 172350 |  |  |  |  | 172350 | 100% |  |  | Article 27 | Survey work and restoration (preservation and restoration) of neglected 450 head and footstones of Sudbury's oldest settlers. |  | On going | Had the initial review completed and currently working on RFP. Items will be incorporated from report (Fannon). | no deadline set
[5 empty] | Town Walkways | 100000 |  |  | 100000 | 100% |  |  |  |  | Article 28 Funded from unrestricted reserve funds. | Engineering, design & construction of walkways. $100,000 from Recreation use |  | completed | Willis Road walkway completed
| Total Appropriated funds 2004 |  |  |  |  | 5590850 | 4718500 |  | 700000 |  | 172350 |  | 0
2005 (FY06) | 7 | 1235961 | 1105972 | 2341933 | Housing Unit Buy Down | 500000 | [6 empty] | 500000 | 100% | Article 42. Funded from housing restricted reserves for $142,343, $200,000 from FY06 revenue, $157,657 from unrestricted reserves. | Purchasing permanent, affordable restrictions on single or multiple family units for homeownership or rental. Not to exceed $100,000 per unit. |  | On going | Going before Town Meeting 2007 to amend Article 42 from 2005 TM. Request change 1) extend time restrictions 2) authorize purchase of no less than 3 units rather than limiting purchases not to exceed $100,000 per unit | $100,000 per unit of housing based upon binding commitments for purchase of restrictions by owners or contract purchasers obtained on or before close of 07TM. Expenditures must be made for purchase of restrictions on or before the close of 08TM.
[5 empty] | Rail Trail Conversion Study | 25000 |  |  | 25000 | 100% |  |  |  |  | Article 43 Funded general unrestricted reserves | Feasibility study on former Penn Central right-of-way. $25,000 from Recreation Category |  | completed | On file
[5 empty] | Cutting Athletic Field | 80250 |  |  | 80250 | 100% |  |  |  |  | Article 44. Allocated to Recreation & funded from general unrestricted reserves | Additional funds for design, site prep, construction of athletic field, parking area, entrance drive and amenities |  | completed
[5 empty] | Willis Pond Dock | 6000 |  |  | 6000 | 100% |  |  |  |  | Article 45. Funded from general unrestricted reserves | Purchase and installation of a dock in Willis Pond at Lake Shore Drive. $6,000 from Recreation category under General Unrestricted Reserves. |  | completed
[5 empty] | Hosmer House | 198900 |  |  |  |  | 198900 | 100% |  |  | Article 47. Funded from historic preservation restricted reserves for $171,250 & FY06 for $27,650. | Restoration phase I. $171,250 from Historic Preservation & Historic Preservation Restricted Reserves & $27,650 from FY06 |  | On going | Ceiling in store room has been removed so structural engineers could have access to beam structure. A structural engineer has been hired to design support structure & elimination of 2 columns and to confirm structural integrity of the building | no deadline set
[5 empty] | Historic Properties Survey II | 9800 |  |  |  |  | 9800 | 100% |  |  | Article 48 allocated to Historic Preservation & funded from FY06 | Completed phase II survey of historic properties. Phase I was done in 1996 with 156 properties listed. |  | On going | HPS II in process. A contract was entered into and work is currently being done. It's believed that 50% complete with data collection portion of the process (per Jim Hill) | no deadline set
[5 empty] | Libby Property | 2660000 | 2660000 | 100% | [6 empty] | Article 49 appropriated $269,000 to pay Debt Service on any bonds or notes during FY06. Allocated to open space & should be funded from open space restricted reserves first and second from general unrestricted reserves if necessary. | Open space acquisition and preservation project of 24.06 acres. Bonded. |  | completed | Bonded/Copy of Deed on file
| Total appropriated Funds 2005 |  |  |  |  | 3479950 | 2660000 |  | 111250 |  | 208700 |  | 500000 |  |  | (Town Meeting Report indicates 3.8 million - $320,000 was an extension of the sunset provisions on previously approved funding from 2003 Community Rental Housing.)
2006 (FY07) | 9 | 1248806 | 1248806 | 2497612 | Carding Mill Pond Harvesting | 32000 | 32000 | 100% | [6 empty] | Article 36. Funded from FY07 | Annual harvest for next four fiscal years of non-native, invasive aquatic weeds in pond. Paid for by Hop Brook Protection Association and reimbursed by Town. |  | On going | Pd $7,669.20 1/24/07 for harvesting summer of 2006. Project continues for 3 more years. Still has $24,330.80 appropriated for next 3 years. | Not to exceed $32,000 for next four years beginning with FY2007.
[5 empty] | Wayside Inn Site Study | 85720 | 42860 | 50% |  |  | 42860 | 50% |  |  | Article 37. Funded from FY07 | Comprehensive study of Longfellow's Wayside Inn 125-acre parcel to be completed by the Wayside Inn Corp. Allocated equally to Open Space and Historic Preservation categories. |  | Completed | Completed and Paid 01/02/07 Certificate of Right of First Refusal is on file. Property survey, property maintenance plan, and signage plan completed. Inn still waiting for final survey-this is beyond CPC funding and responsibility of Inn.
[5 empty] | Mahoney and Melone Feasibility studies | 50000 |  |  | 25000 | 50% |  |  | 25000 | 50% | Article 38. Allocated equally to Community Housing & Recreation & funded from FY07 | Feasibility studies of 2 town-owned properties for future CPA uses, including housing and recreation |  | On Going | RFP being developed for feasibility study for both sites. Arc-495 is conducting a mix use study on Melone site. Study will be complete by May 2007 | no time limit specified
[5 empty] | Walkway Construction | 100000 |  |  | 100000 | 100% |  |  |  |  | Article 39. Allocated to recreation & funded from FY07 | Engineering, design & construction of walkways. $100,000 from Recreation use |  | On Going | Walkway being selected at Town Meeting April 2007 | no time limit specified
[5 empty] | Loring Parsonage Exterior Restoration | 74281 |  |  |  |  | 74281 | 100% |  |  | Article 40. Allocated to Historic Preservation & funded from FY07 | Restoration of exterior of Loring Parsonage. |  | Not started yet | On the back burner for awhile as the building was occupied (per Lynn 3/12/07) HC has to put project on hold while the Sudbury Foundation had to move into building while building was renovated. The HC feels the scope of the project would make it difficult for a tenant to be in the building during restoration work. Intention of the SHC's to start bid process when a commitment for when the Foundation was moving out. Potentially the Credit Union may be moving in, but the HC doesn't have details yet. HC will speak to Maureen to get an understanding of her current plans and timelines so project can be fit around Maureen's plan. (Per Jim Kelly and Jim Hill) | Work to be completed by end of FY08
[5 empty] | Hearse House Relocation and Restoration | 24022 |  |  |  |  | 24022 | 100% |  |  | Article 41. Allocated to Historic Preservation & funded from FY07 | Relocation of historic hearse house to town land. Building donated by current owners, 2 Sudbury contractors are donating their labor, Town DPW performing some services. House to be reconstructed adjacent to Town Pound on Concord Road |  | On going | Building disassembled and transferred to new location. Foundation completed (by Town Public Works Dept). Some timbers moved to foundation. Will be assembled in April 2007 and will take 2 weeks. Want to duplicate iron work on hinges etc…Will work with the Public Works Dept. to bring electricity to the building as it nears completion. | Work to be completed by end of FY08
[5 empty] | Cemetery Ironwork Restoration | 136305 |  |  |  |  | 136305 | 100% |  |  | Article 42. Funded from FY07 for $58,837 and $77,468 from Historic Restricted Reserves | Restoration of historic decorative ironwork located in Revolutionary and Wadsworth cemeteries and at tombs alongside Concord Road in Town Center. |  | On going | Going out to bid this coming week. Expected to be completed prior to next winter. (per Jim Hill 3/14/07) | Work to be completed by end of FY08
[6 empty] | -320000 | [6 empty] | -320000 |  | transfer of $320,000 from 2003 TM Article 32C, amended by 2005 TM Article 41
[5 empty] | Sudbury Housing Authority - Community Housing | 360000 | [6 empty] | 360000 | 100% | Article 43. Funded from FY07 for $40,000 & transfer of $320,000 from 2003 TM Article 32C, amended by 2005 TM Article 41 | Down Payments on purchase of existing or to be built housing units within town | Down payments on purchase of existing or to be built housing units within town. | On going | May purchase 2 units in phase 1 in 2007 at Old County Road/ Then may purchase 2 more units in phase 2. $90,000 each unit | Purchases to be completed by end of FY09
[5 empty] | L-S Community Athletic Field | 960000 |  |  | 960000 | 100% |  |  |  |  | Article 44. Funded from FY06 general unrestricted reserves | Construction of new synthetic-turf athletic field and track on grounds of Lincoln-Sudbury Regional High School. New lighting and bleachers. L-S provided $190,000 and athletic user groups $350,000. |  | On Going | Paid in Full | Work to be completed by end of FY08
Total Appropriated Funds 2006 | [5 empty] | 1502328 | 74860 |  | 1085000 |  | 277468 |  | 65000
2007 (FY08) | 6 | ? | ? | ? | Bruce Freeman Rail Trail Title Search | 15000 |  |  | 15000 | 100% |  |  |  |  | Article 22. Allocated to recreation category & funded from unrestricted reserves | Title search of north-south railroad right of way owned by Commonwealth of Mass. & running from intersection with the east-west MBTA railroad right of way north of Concord border. |  |  |  | Work to be completed by FY10
[5 empty] | Bruce Freeman Rail Trail Wildlife Study | 25000 |  |  | 25000 | 100% |  |  |  |  | Article 23. Allocated to recreation category & funded from FY08 revenue | 4 season study of wildlife & rare species habitats along railway described in Art. 22. |  |  |  | Work to be completed by FY10 and funds to be expended for study only after a satisfactory title search authorized under Article 22.
[5 empty] | Bruce Freeman Rail Trail Existing Conditions Base Map | 105000 |  |  | 105000 | 100% |  |  |  |  | Article 24. Allocated to Recreation category & funded from FY08 revenue | Environmental Resource Delineation & existing conditions base map of described railway in Art. 22. |  |  |  | Work to be completed by FY10 and funds to be expended for study only after a satisfactory title search authorized under Article 22.
[5 empty] | Sudbury Housing Trust Allocation | 385000 | [6 empty] | 385000 | 100% | Article 26. Allocated to Community Housing Category $250,000 from FY8 CPA revenue & balance of Community Housing Reserve funds retained from prior years ($135,000). | Sudbury Housing Trust created at 2006 TM. This appropriation is first funding for the Trust. |  |  |  | no time limit given
[5 empty] | Carding Mill House | 25000 |  |  |  |  | 25000 | 100% |  |  | Article 28. Allocated to Historic category & funded from FY08 Revenue | Work to secure house & weather tight & architectural & engineering studies as a planning base for future use of property. |  |  |  | no time limit given
[5 empty] | Town Center | 30000 | 10000 | 33.33% | 10000 | 33.33% | 10000 | 33.33% |  |  | Article 29. Allocated equally to the Historic, Recreation and Open Space categories. | Partially funding survey & engineering work |  |  |  | no time limit given
Total Appropriated Funds 2007 | [5 empty] | 585000 | 10000 |  | 155000 |  | 35000 |  | 385000
Total Appropriated funds since adoption of CPA ** | [5 empty] | 11959728 | 100%
Total Open Space | [5 empty] | 7854960 | 65.68% | [8 empty] | Note: *Although a 100% State match has typically been awarded, amounts may differ from tax surcharge. State Match is based on Sudbury's tax surcharge estimate. State match is given in October before the end of the Sudbury's Fiscal Year and before 4th quarter taxes have been collected. Also taxes collected may be less if deliquencies exist. **Appropriations may be more than total revenue due to bonded projects.
Total Recreation | [5 empty] | 2051250 | 17.15% |  |  |  | Debt (Bonded Projects)
Total Historic Preservation | [5 empty] | 783518 | 6.551% |  |  |  | Project | Date issued | Amount issued
Total Community Housing | [5 empty] | 1270000 | 10.62% |  |  |  | Dickson | 2004-06-10 | 430000
[11 empty] | Cutting | 2004-06-10 | 5318500
Total Revenue from Tax surcharge & State Match * | [5 empty] | 10174323 |  |  |  |  | Libby | 2005-06-15 | 2660000 | *** | Per Sudbury Accounting. Amount listed in TM Proceedings state's $2,690,000
Total Tax Surcharge | [5 empty] | 5697933
Total State Match | [5 empty] | 4476390