## Sudbury
MHC# | Feature | Milepost | Proposed Action | Proposed Project Activity
Newly identified contributing resource (not included on SUD.R inventory form)
| Electric switch box | 19.75 | R&R | Remove & reset
Contributing resources on SUD.R inventory form that could not be located by SHC/Spies, but were located by Eversource/DCR
| Farm Crossing (2 concrete & rebar posts) | 18.79 | Avoid | Outside limit of work
| Culvert 125B | 18.73 | Extend | Extend existing pipe to maintain vernal pool hydrology. | Remove | 2
Contributing resources on SUD.R inventory form that were located by both SHC/Spies and Eversource/DCR
SUD.936 | Culvert 126A | 18.96 | Avoid | Clear out sediment | Replace | 2
SUD.937 | Milepost N-85/B-19 | 19 | Avoid | Outside limit of work | Rehab | 1
SUD.938 | Culvert 126B | 19.06 | Avoid | Cut vegetation on northeast wingwall that is causing collapse (no grubbing). | Extend | 1
SUD.939 | Rail Rest | 19.21 | R&R | Remove & reset | Avoid | 38
SUD.940 | Culvert 126D | 19.22 | Avoid | Outside limit of work | Avoid / R&R | 14
SUD.942 | Battery Well for Distant Approach Signal | 19.26 | Avoid/R&R | Avoid; if not possible, remove and reset. | R&R | 13
SUD.941 | Distant Approach Signal | 19.26 | R&R | Remove & reset | Total | 71 | * including 4 archaeological sites, two resources included on Spies' inventory but were not located nor given MHC inventory numbers, and one new resource (electric switch box) that was identified recently by CHG/VHB.
SUD.943 | Signal Relay Box | 19.37 | R&R | Remove & reset
SUD.901 | Bridge 127 | 19.47 | Replace | Replace superstructure (top two courses of stone abutments to be removed; other courses to remain).
SUD.944 | Poured Concrete base for Signal Relay Box/Battery Well | 19.6 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.945 | Culvert 127A | 19.7 | Replace | Replace with 24" ductile iron pipe (“DIP”) with concrete headwall.
SUD.946 | Whistle Post | 19.73 | Avoid | Outside limit of work
SUD.282 | Section Tool House | 19.75 | Avoid | Outside limit of work
SUD.947 | Concrete base for Auto Highway Flashers | 19.76 | Avoid | Outside limit of work
SUD.949 | Signal Relay Box (mast only) | 19.76 | Avoid | Outside limit of work
SUD.948 | Concrete base for Auto Highway Flashers | 19.76 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.950 | Culvert 127B | 19.87 | Avoid | Outside limit of work
SUD.951 | Concrete Bases for Highway Signal | 19.97 | Avoid | Outside limit of work
SUD.952 | Concrete Sign Post | 19.98 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.396 | South Sudbury Station | 19.99 | Avoid | Avoid
SUD.954 | 3 Switch Stands | 20 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.955 | Concrete bases & steel posts for Signal/Electrical boxes (5) | 20 | R&R | Remove & reset
SUD.953 | Milepost | 20 | R&R | Remove & reset
SUD.956 | Diamond junction with Framingham & Lowell RR | 20.02 | R&R | Remove & reset
SUD.957 | Wood whistle/stop sign post | 20.02 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.959 | Concrete Base for Signal E2 | 20.07 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.958 | Signal Relay Box | 20.07 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.960 | Rail Rest | 20.09 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.961 | Signal Relay Box | 20.13 | Avoid | Outside limit of work
SUD.962 | Culvert 127C | 20.14 | Avoid | Outside limit of work
SUD.963 | Signal Relay Box | 20.34 | R&R | Remove & reset
SUD.964 | Wood Post | 20.34 | Avoid | Outside limit of work
SUD.965 | Tall Concrete Sign Post | 20.39 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.966 | Culvert 127D | 20.44 | Avoid | Outside limit of work
SUD.967 | Rail Rest | 20.55 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.968 | Signal Relay Box | 20.59 | R&R | Remove & reset
SUD.969 | Whistle Post | 20.63 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.970 | Culvert 127E | 20.75 | Avoid | Outside limit of work
SUD.972 | Signal Relay Box | 20.79 | Avoid | Outside limit of work
SUD.971 | Crossing Sign Base | 20.79 | R&R | Remove & reset
SUD.974 | Battery Well for Interlocking Signal #M208 | 20.8 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.973 | Distant Approach Interlocking Signal #M208 | 20.8 | Avoid | Outside limit of work
SUD.975 | Rail Rest | 20.98 | R&R
SUD.976 | Milepost B21 N83 | 21 | Avoid | Outside limit of work
SUD.977 | Whistle Post | 21.13 | Avoid | Outside limit of work
SUD.978 | Signal Relay Box | 21.16 | Avoid/R&R | Avoid; if not possible, remove and reset.
SUD.979 | Culvert 127F | 21.18 | Avoid | Outside limit of work
SUD.980 | Wood Post North Side of ROW | 21.29 | R&R
SUD.981 | Auto Highway Flashers/Signal Relay Cabinet | 21.35 | Avoid | Outside limit of work
SUD.982 | Wood Post, south side of ROW | 21.36 | Avoid | Outside limit of work
SUD.983 | Culvert 127G | 21.4 | Avoid | Outside limit of work
SUD.984 | Culvert 127H | 21.51 | Avoid | Cut two 12" trees that are causing wingwall damage (no grubbing).
SUD.985 | Culvert 127I | 21.58 | Avoid | Clear out debris on north end.
SUD.986 | Whistle Post | 21.58 | Avoid | Outside limit of work
SUD.987 | Whistle Post | 21.66 | Avoid | Outside limit of work
SUD.988 | Rail Rest | 21.94 | R&R
SUD.989 | Milepost B22 N82 | 22 | Avoid | Outside limit of work
SUD.990 | Culvert 127J | 22.05 | Avoid | Outside limit of work
SUD.991 | Whistle Post | 22.19 | Avoid | Outside limit of work
SUD.900 | Bridge 128 | 22.24 | Rehab | Upgrade bridge deck to support trail & transmission line (removal of small portion of stone abutments on south side of both east and west abutments; other portions to remain )
SUD.992 | Culvert 129A | 22.83 | Avoid | Outside limit of work
SUD.935 | Telegraph Poles | Throughout | Avoid | Outside limit of work
SUD.933 | Rails | Throughout | Remove | Remove
SUD.934 | Wood Ties | Throughout | Remove | Remove
SUD-HA-39 | East Sudbury Station Archaeological Site | 18.84 | Avoid & protect | Protect with geotextile fabric & fill.
SUD-HA-37 | Section Tool House Archaeological Site | 19.75 | Avoid & protect | Outside limit of work
SUD-HA-26 | South Sudbury Station Archaeological Site | 19.99 | Avoid & protect | Outside limit of work
SUD-HA-38 | Wayside Inn Archaeological Site | 21.9 | Avoid & protect | Outside limit of work
Contributing resources on SUD.R inventory form that could not be located by SHC/Stacy Spies or Eversource/DCR
XXX | Signal Relay Box | 18.39?
XXX | Culvert 126C | 19.28?
XXX | Whistle Post | 22.?

## Hudson
MHC# | Feature | Milepost | Proposed Action | Proposed Project Activity
| Rails | Througout | Remove | Remove
| Ties | Througout | Remove | Remove | Remove | 3
| Telegraph Pole | 23.06 | Avoid | Outside limit of work | Replace | 1
| Milepost | 23 | Avoid | Outside limit of work | Rehab | 0
| Railrest | 23.05 | R&R | Remove & reset | Extend | 0
| Conduit Pipe Derail Switch | 23.33 | R&R | Remove & reset | Avoid | 10
| Stone wall | 23.95 | Remove | Remove | Avoid & protect | 2
| Section post | 24 | R&R | Remove & reset | Avoid / R&R | 3
| Milepost | 24 | Avoid | Outside limit of work | R&R | 9
| Railrest | 24.09 | R&R | Remove & reset | Total | 28 | * includes 2 archaeological sites
HUD.HA-9 | Ordway Station Archaeological Site | 24.1 | Avoid & protect | Outside limit of work
| Culvert 129C | 24.3 | Avoid | Remove tree on northeast corner; stabilize bank
| Concrete base well | 24.36 | Avoid | Outside limit of work
| Whistle post (S) | 24.4 | R&R | Remove & reset
| Whistle post (N) | 24.5 | R&R | Remove & reset
| Wood Post | 24.72 | R&R | Remove & reset
| Utility Pole | 24.76 | Avoid | Outside limit of work
| Wood Post | 24.78 | Avoid/R&R | Avoid; if not possible, remove and reset.
| Track Switch Stand with Electrical Box | 24.8 | Avoid/R&R | Avoid; if not possible, remove and reset.
| Concrete Box | 24.89 | R&R | Remove & reset
| Railrest | 25 | R&R | Remove & reset
| Milepost | 25 | Avoid | Outside limit of work
HUD.908 | Bridge #130 | 25.37 | Replace | Replace superstructure (no existing abutments)
HUD.HA-8 | Gleasondale Station Archeological Site | 25.64 | Avoid & protect | Protect with geotextile fabric & fill.
| Cattle pass | 25.83 | Avoid | Remove rails and ties on top of cattle pass
| Railrest | 26 | Avoid/R&R | Avoid; if not possible, remove and reset.
| Milepost | 26 | Avoid | Outside limit of work
| Culvert 132A | 26.12 | Avoid | Outside limit of work